## RE 2020-21 (ITI) (2) (hidden)
Form B-12
Statement of Ongoing and New works for the finanacial year 2020-21
Department : Skill Development J&K
Office : Directorate of Skill Development, J&K
Demand No. : 34
Major Head : 4250
Sub Major Head : 00
Minor Head : 800
Group Head : 0011
Sub Head : 1644
Detailed Head : 115
Capex Budget 2020-21
S.No | Name of the work/ activity-wise | District | Executing Agency | Executing Agency | Project Initiation Year | Orginal Cost of the Project | Revised Cost | Whether AA/TS accorded if Yes , No. & Date | Cummulative Exp. Ending 31st March, 2020 | Approved Capex Budget | Expenditure ending September, 2020 | Anticipated Exp. Ending March 2021 | Proposed Capex Budget for ensuing Year | Com. Ant. Expdt. 03/2021 | Balace reqd | Physical Status
ITI Sector
Ongoing Works
1 | Construction of W/ shop for Motor Mehanic (MMV) / Plumber Trade & auto mobile service Station at IT R.S.Pora | Jammu | R&B | PWD (R&B) | 2015-16 | 93.3 | 93.3 | 201 of 2016 17.03.2016 | 81.86 | 5.72 | 2.86 | 11.44 | 0 | 93.3 | 0 | Completed
2 | Construction of Hostel Building at ITI Banihal | Ramban | JK Housing Board | J&K Housing Board | 2014-15 | 86.16 | 86.16 | 178 of 2014 dated:- 21-02-2014 | 77.83 | 4.17 | 0 | 8.33 | 0 | 86.16 | 0 | Completed
3 | Construction of first floor to ITI building at ITI Nowshera | Jammu | R&B | PWD (R&B) | 2018-19 | 99.9 | 99.9 | 38 of 2019 dated:- 17-01-2019 | 39.06 | 30.42 | 0 | 30.42 | 30.42 | 69.48 | 30.42 | 60% Completed
4 | Construction of Toilet Blocks for Male and Female Trainees at ITI Kathua | Kathua | R&B | PWD (R&B) | 2018-19 | 11.09 | 11.09 | 36 of 2019 dated:- 17-10-2019 | 3.41 | 2.79 | 0 | 7.68 | 0 | 11.09 | 0 | Completed
5 | 100 KVA Servo Stablizer with Panel & Shed at ITI Kishtwar | Kishtwar | JKPDC | JKPDC | 2018-19 | 16 | 16 | 671 of 2018 dated:- 28-08-2018 | 8.88 | 3.56 | 0 | 7.12 | 0 | 16 | 0 | Completed
6 | Construction of Conference / Examination Hall at ITI Anantnag | Anantnag | Engineering Wing DTE | Engineering Wing, DSD | 2011-12 | 33.06 | 67 | 124 of 2016 dated:- 25-02-2016 | 42.87 | 10 | 0 | 9 | 15.13 | 51.87 | 15.13 | Completed
7 | Construction of Computer cum Language lab at ITI Anantnag | Anantnag | Engineering Wing DTE | Engineering Wing, DSD | 2013-14 | 66.97 | 66.97 | 37 of 2014 dated:- 16-01-2014 | 56.06 | 5.46 | 0 | 0 | 5.46 | 56.06 | 10.91 | Completed
8 | Construction of Computer cum Language lab at ITI Pattan | Baramulla | Engineering Wing DTE | Engineering Wing, DSD | 2013-14 | 66.97 | 66.97 | 36 of 2014 dated:- 16-01-2014 | 64.32 | 1.3 | 0 | 0 | 1.35 | 64.32 | 2.65 | Completed
9 | Construction of Computer cum Language lab at Women ITI Rohama | Baramulla | Engineering Wing DTE | Engineering Wing, DSD | 2013-14 | 67.32 | 67.32 | 38 of 2014 dated:- 16-01-2014 | 36.19 | 15.57 | 0 | 10 | 15.56 | 46.19 | 21.13 | 70% Completed
10 | Construction of Workshop Block at ITI Uri | Baramulla | Engineering Wing DTE | Engineering Wing, DSD | 2013-14 | 93.81 | 93.81 | 39 of 2014 16.01.2014 | 87.29 | 3.26 | 0 | 3.26 | 3.26 | 90.55 | 3.26 | 80% Completed
11 | Construction of Ist Floor over the existing ground floor of workshop building at ITI Kupwara | Kupwara | Engineering Wing DTE | Engineering Wing, DSD | 2011-12 | 97.64 | 97.64 | 125 of 2016 dated:- 25-02-2016 | 95.99 | 1.65 | 0 | 1.65 | 0 | 97.64 | 0 | Completed
12 | Construction of Additional Hostel accommodation at ITI Poonch | Poonch | Engineering Wing DTE | Engineering Wing, DSD | 2011-12 | 57.62 | 57.62 | 829 of 2012 dated:- 13-12-2012 | 41.74 | 7.94 | 0 | 0 | 7.94 | 41.74 | 15.88 | 90% Completed
13 | Construction of Computer cum Language Lab at ITI Kulgam | Kulgam | Engineering Wing DTE | Engineering Wing, DSD | 2013-14 | 66.97 | 66.97 | 34 of 2014 dated:- 16-01-2014 | 26.68 | 20.15 | 0 | 10 | 30.29 | 36.68 | 30.29 | 60% Completed
14 | Construction of Computer cum Language Lab at ITI Kathua | Kathua | Engineering Wing DTE | Engineering Wing, DSD | 2013-14 | 69.05 | 69.05 | 31 of 2014 16.01.2014 | 49.59 | 9.71 | 0 | 0 | 9.73 | 49.59 | 19.46 | 60% Completed (Funds not received)
15 | Construction of Toilet Block at ITI Women Jammu | Jammu | R&B | PWD (R&B) | 2019-20 | 6.1 | 6.1 | 413 of 2019 dated:- 04-07-2019 | 2.66 | 3.21 | 0 | 3.44 | 0 | 6.1 | 0 | 50% Completed
16 | Construction of approach road from Main Gate at ITI Bhaderwah | Doda | R&B | PWD (R&B) | 2019-20 | 15 | 15 | 629 of 2019 dated:- 07-11-2019 | 4 | 5.5 | 0 | 11 | 0 | 15 | 0 | 50% Completed
17 | Installation of Three Phase Electric Connection at ITI Banihal | Ramban | JKPDC | JKPDC | 2019-20 | 6.71 | 6.71 | 412 of 2019 dated:- 04-07-2019 | 0 | 4.5 | 0 | 6.71 | 0 | 6.71 | 0 | u/ Progress
18 | Establishment of Conference Hall at Directorate of Technical Education, Jammu | Jammu | JKI | JKI | 2019-20 | 14.51 | 14.51 | 415 of 2019 dated:- 04-09-2019 | 0 | 12 | 0 | 12 | 2.51 | 12 | 2.51 | 80% Completed
19 | Construction of Library/Drawing Hall at ITI Bhaddu/Billawar | Kathua | Engineering Wing DTE | Engineering Wing, DSD | 2011-12 | 36.17 | 36.17 | 827 of 2012 dated:- 13-12-2012 | 29.99 | 3.09 | 0 | 0 | 3.09 | 29.99 | 6.18 | 80% Completed
| Sub-Total A |  |  |  |  | 1004.35 | 1038.29 | 0 | 748.42 | 150 | 2.86 | 132.05 | 124.74 | 880.47 | 157.82
New Works
1 | Construction of Boundary Wall and Main Gate of Devry Stones at Govt. ITI Kulgam | Kulgam | Housing Board | J&K Housing Board | 2020-21 | 31.57 | 31.57 | 67 of 2020 dated:- 13-02-2020 | 0 | 0 | 0 | 20 | 11.57 |  |  | Proposed under RE
2 | Construction of workshop block at Women ITI Bemina- Phase-II | Srinagar | R&B | PWD (R&B) | 2020-21 | 82.58 | 82.58 | 681 of 2019 dated:- 03-12-2019 | 0 | 0 | 0 | 82.58 | 0 |  |  | Proposed under RE
3 | Balance cost for completion of 3- storey workshop building and reconstruction of damaged compound walling at ITI Zainakote | Srinagar | Housing Board |  | 2020-21 | 136 | 136 | No | 0 | 0 | 0 | 136 | 0 |  |  | U/Process
| Sub-Total B |  |  |  |  | 250.15 | 250.15 | 0 | 0 | 0 | 0 | 238.58 | 11.57
Maintenance of Capital Assets (M&R)
1 | Face lifting of Main building including Repair to toilets & Bathroom of Hostel Building of ITI Hiranagar | Kathua | R&B | PWD (R&B) | 2018-19 | 9.06 | 9.06 | 716 of 2018 dated:- 15-09-2018 | 4.53 | 4.53 | 0 | 4.53 | 0 | 9.06 | 0 | Completed
2 | Landscape development of ITI Sopore. Construction of fencing around park proposed in front of administration and women's building | Baramulla | R&B | PWD (R&B) | 2018-19 | 3.19 | 3.19 | 715 of 2018 dated:- 15-09-2018 | 2.34 | 0.85 | 0 | 0.85 | 0 | 3.19 | 0 | Completed (Funds not received)
3 | Dismantling of old abandoned Block at Govt. ITI Samba | Samba | R&B | PWD (R&B) | 2019-20 | 3 | 2.4 | 409 of 2019 dated:- 04-07-2019 | 2.4 | 0.6 | 0 | 0 | 0 | 2.4 | 0 | Completed
4 | Development & Upgradation of parking area at ITI Jammu | Jammu | R&B | PWD (R&B) | 2020-21 | 10.92 | 10.92 | 350 of 2020 dated:- 29-09-2020 | 0 | 10.92 | 0 | 10.92 | 0 | 10.92 | 0 | under Tendering Process
5 | Facelifting of Admn Block & Workshop Block at Women ITI Jammu | Jammu | R&B | PWD (R&B) | 2020-21 | 11.92 | 11.92 | No | 0 | 11.92 | 0 | 11.92 | 0 | 11.92 | 0 | Funds not released
6 | Repair of main block at ITI Doda | Doda | R&B | PWD (R&B) | 2020-21 | 2 | 2 | 298 of 2020 dated:- 09-09-2020 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | u/ Progress
7 | Repair & Renovation of Workshop / Adm/ Hostel Block ofITI kulgam | Kulgam | R&B | PWD (R&B) | 2020-21 | 8.43 | 8.43 | 359 of 2020 dated:- 06-10--2020 | 0 | 15 | 0 | 8.43 | 0 | 8.43 | 0 | u/ Process
8 | Facelifting of ITI building at ITI Kangan | Ganderbal | R&B | PWD (R&B) | 2020-21 | 8.85 | 8.85 | 297 of 2020 dated:- 09-09-2020 | 0 | 8.85 | 0 | 8.85 | 0 | 8.85 | 0 | Work alloted
9 | Repair of protection wall & Iron fencing grill at ITI Kupwara | Kupwara | R&B | PWD (R&B) | 2020-21 | 6.15 | 6.15 | 299 of 2020 dated:- 09-09-2020 | 0 | 6.15 | 0 | 6.15 | 0 | 6.15 | 0 | Work alloted
10 | Renovation (including electrification) of Workshop block at ITI K B Pora | Kulgam | R&B | PWD (R&B) | 2020-21 | 10 | 10 | 296 of 2020 dated:- 09-09-2020 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | u/ Progress
11 | Repair/renovation of ITI Jammu | Jammu | __ | PWD (R&B) | 2019-20 | 2.37 | 2.37 | 101 of 2020 dated 26.02.2020 | 0 | 2.37 | 0 | 2.37 | 0 | 2.37 | 0 | Completed (Funds not received)
12 | Replacement of Secuirity lights ( Sodium Vapour Lights) and Garden lights by way of LED lights in the campus of ITI Anantnag | Anantnag | __ | New Work | 2020-21 | 3.48 | 3.48 | No | 0 | 3.48 | 0 | 3.48 | 0 | 3.48 | 0 | Funds not released
13 | Augmentation of 25 KVA to 63 KVA DT at Women ITI Kangan | Ganderbal | __ | New Work | 2020-21 | 2.75 | 2.75 | No | 0 | 2.75 | 0 | 2.75 | 0 | 2.75 | 0 | Funds not released
14 | Repair work of Roof Tiles and expansion joints of old Blocks at ITI R.S.Pora | Jammu | __ | New Work | 2020-21 | 1.29 | 1.29 | No | 0 | 1.29 | 0 | 1.29 | 0 | 1.29 | 0 | Funds not released
15 | Replacement of Sodium Vapour Lights by way of LED lights in the campus of ITI Seer Hamdan | Anantnag | __ | New Work | 2020-21 | 4.82 | 4.82 | No | 0 | 4.82 | 0 | 4.82 | 0 | 4.82 | 0 | Funds not released
16 | Repair and renovation of Pre-Fab Structure by way of Ceramic tiles flooring ,Doors and Windows, Electric Works and Painting work at R.S. Pora | Jammu | __ | New Work | 2020-21 | 0.79 | 0.79 | No | 0 | 0.79 | 0 | 0.79 | 0 | 0.79 | 0 | Funds not released
17 | White Washing / Face lifting of DSD office at Bikram Chowk Jammu | Jammu | __ | New Work | 2020-21 | 2 | 2 | No | 0 | 2 | 0 | 2 | 0 | 2 | 0 | Funds not released
18 | White Washing/Face lifting of DSD office at Bemina Srinagar | Srinagar | __ | New Work | 2020-21 | 2 | 2 | No | 0 | 2 | 0 | 2 | 0 | 2 | 0 | Funds not released
19 | Renovation of Hostel Block at ITI building, Shopian | Shopian | __ | New Work | 2020-21 | 9.68 | 9.68 | No | 0 | 9.68 | 0 | 9.68 | 0 | 9.68 | 0 | Funds not released
20 | Royality on account of earth filling at ITI Zainakote | Srinagar | __ |  | 2020-21 | 10 | 10 | No | 0 | 0 | 0 | 10 | 0 | 10 | 0 | New Work
| Sub-Total C |  |  |  |  | 112.7 | 112.1 | 0 | 9.27 | 100 | 0 | 102.83 | 0 | 112.1 | 0
Machinery & Equipments
1 | Upgradation of Machinery & Equipment of Govt. ITIs . | J&K | J&K | Not applicable | 2020-21 | 912 | 912 | NA | 0 | 912 | 0 | 600 | 500 |  |  | Funds not released
| Sub-Total D |  |  |  |  | 912 | 912 |  |  | 912 | 0 | 600 | 500
Material and supply
1 | Procurement of Material & Supply | J&K | J&K | Not applicable | 2020-21 | 110 | 110 | NA | 0 | 110 | 0 | 50 | 200 |  |  | Funds not released
| Sub-Total E |  |  |  |  | 110 | 110 |  |  | 110 | 0 | 50 | 200
Non-Construction Work
1 | Heritage Craft Courses | J&K | J&K | Not applicable | 2020-21 | 250 | 250 | NA | 0 | 250 | 0 | 220 | 250 |  |  | Funds not released
2 | Land compensation | Ramban | Ramban | Not applicable | 2020-21 | 407 | 407 | NA | 276.31 | 125 | 0 | 30.69 | 100 |  |  | Funds not released
3 | Farm ITIs |  |  | Not applicable | 2020-21 | 376.87 | 376.87 | NA | 0 | 0 | 0 | 68.92 | 307.95
4 | STRIVE (100 % CSS) |  |  | Not applicable | 2020-21 | 255 | 255 | NA | 0 | 0 | 0 | 255 | 0
| Sub-Total F |  |  |  |  | 1288.87 | 1288.87 |  |  | 375 | 0 | 574.61 | 657.95
| G. Total (A+B+C+D+E+F) |  |  |  |  | 3678.07 | 3711.41 |  | 757.69 | 1647 | 2.86 | 1698.07

## RE 2020-21 (POLY) (2) (hidden)
Form B-12
Statement of Ongoing and New works for the finanacial year 2020-21
Department : Skill Development J&K
Office : Directorate of Skill Development, J&K
Demand No. : 34
Major Head : 4202
Sub Major Head : 02
Minor Head : 105
Group Head : 0011
Sub Head : 1511
Detailed Head : 115
Capex Budget 2020-21
S.No | Name of the work/ activity-wise | District | Executing Agency | Executing Agency | Project Initiation Year | Orginal Cost of the Project | Revised Cost | Whether AA/TS accorded if Yes , No. & Date | Cummulative Exp. Ending 31st March, 2020 | Approved Capex Budget | Expenditure ending September, 2020 | Anticipated Exp. Ending March 2021 | Proposed Capex Budget for ensuing Year | ant. com. Expdt 03/2020 | Balance Cost | Physical Status
Polytechnic Sector
Ongoing Works
1 | Construction of staff residential quarters at Govt. Polytechnic for Women Jammu. | Jammu | Engineering wing of DTE | Engineering wing, DSD | 2012-13 | 71 | 71 | 14 Tech-Edu of 2013 17.01.2013 | 65.82 | 5.18 | 0 | 5.18 | 0 | 71 | 7.1054e-15 | Completed ( Funds not received)
2 | Repair/renovation of flood damaged auditorium at K.G. Polytechnic, Srinagar. | Srinagar | R&B | PWD (R&B) | 2017-18 | 30.16 | 31.33 | 26 of 2020 dated 14.01.2020 | 30.16 | 1.17 | 0.59 | 1.17 | 0 | 31.33 | -1.7764e-15 | Completed
3 | Construction of deficient infrastructure as per AICTE Norms in existing Polytechnics to avoid de-recognition/disapproval of courses. | J&K | R&B | PWD (R&B) | 2017-18 | 148.65 | 148.65 | 914 of 2018 dated:- 14-12-2017 | 104.42 | 44.23 | 0 | 44.23 | 0 | 148.65 | 0 | Completed ( Funds not received)
4 | Construction of Hostel at Govt Polytechnic Boys Jammu | Jammu | R&B | PWD (R&B) | 2018-19 | 717.4 | 717.4 | 15-Edu (Tech) of 2019 dated:- 13-03-2019 | 131.14 | 144.83 | 60 | 200 | 250 | 331.14 | 386.26 | 40% completed
5 | Construction of Hostel at Govt. Polytechnic at Anantnag(Civil Construction) | Anantnag | __ | JKPCC (proposed) | 2019-20 | 764 | 764 | No | 0 | 80 | 0 | 80 | 100 | 80 | 684 | U/process
6 | Establishment of Conference Hall at Directorate of Technical Education, Srinagar. | Srinagar | R&B | JKI | 2019-20 | 16.58 | 16.58 | 414 of 2019 dated 04.09.2019 | 0 | 16.58 | 0 | 8.29 | 8.29 | 8.29 | 8.29 | U/process
7 | Construction of Boundary wall at Govt. Polytechnic Budgam. | Budgam | R&B | PWD (R&B) | 2018-19 | 54.01 | 54.01 | 674 of 2018 dated:-28-08-2018 | 38.13 | 8.01 | 1.5 | 8.01 | 0 | 46.14 | 7.87 | 80% Completed
| Sub-Total A |  |  |  |  | 1801.8 | 1802.97 | 0 | 369.67 | 300 | 62.09 | 346.88 | 358.29 | 716.55 | 1086.42
New Works
1 | Establishment of CIIIT at Govt. Polytechnic (Boys) Jammu | Jammu | R&B | PWD (R&B) | 2020-21 | 276.7 | 261.93 | 178 of 2020 dated:- 27-05-2020 | 0 | 250 | 50 | 261.93 | 0 | 261.93 | 0 | 50% Completed
2 | Establishment of CIIIT at Govt. Polytechnic Baramulla | Baramulla | R&B | PWD (R&B) | 2020-21 | 392.52 | 405.36 | 189 of 2020 dated:- 09-06-2020 | 0 | 392.52 | 196.26 | 405.36 | 0 | 405.36 | 0 | 75% completed
3 | Electrification & other minor works of Main building/ workshop building at Govt. Polytechnic Budgam | Budgam | JKPCC |  | 2020-21 | 75 | 75 | No | 0 | 0 | 0 | 75 | 0 |  |  | U/process
| Sub-Total B |  |  |  |  | 744.22 | 742.29 | 0 | 0 | 642.52 | 246.26 | 742.29 | 0
Maintenance of Capital Assets (M&R)
1 | Repair and Renovation of Principal Quarter at Govt. Polytechnic Boys Jammu. | Jammu | R&B | Engineering wing, DSD | 2017-18 | 4.41 | 4.41 | 72 of 2018 dated:- 04-01-2018 | 2.6 | 1.6 | 0 | 0 | 1.81 | 2.6 |  | Completed
2 | Repair/Renovation of Conference Hall of Women Polytechnic Jammu. | Jammu | SICOP | JK SICOP | 2018-19 | 16.53 | 16.53 | 670 of 2018 dated:- 28-08-2018 | 8.9 | 7.63 | 3.82 | 7.63 | 0 | 16.53 |  | Completed
3 | Renovation of Hostel (New Block) at K G Polytechnic College Gogji Bagh Srinagar. | Srinagar | R&B | PWD (R&B) | 2017-18 | 19.12 | 21.46 | 117 of 2020 dated 10.03.2020 | 19.12 | 2.34 | 1.17 | 2.34 | 0 | 21.46 | 0 | completed
4 | Electrification of Internal wiring (3 Phase) to workshop building at Polytechnic Anantnag. | Anantnag | R&B | PWD (R&B) | 2020-21 | 10.33 | 10.33 | 212 of 2020 dated 30.06.2020 | 0 | 10.33 | 5.17 | 10.33 | 0 | 10.33 | 0 | 60% Completed
5 | Repair/Renovation of DTE office Srinagar (Phase-II). | Srinagar | R&B | Engineering wing, DSD | 2018-19 | 3.69 | 3.69 | 719 of 2018 dated:- 15-09-2018 | 3.35 | 0.34 | 0 | 0 | 0 | 3.35 | 0 | Completed
6 | Civil Work of Auditorium at KGP Srinagar inculding painting/ polising at Kashmir Govt Polytechnic. | Srinagar | R&B | PWD (R&B) | 2020-21 | 10.35 | 10.35 | 27 of 2020 dated 14.01.2020 | 0 | 5.58 | 0 | 10.35 | 0 | 10.35 | 0 | Funds not received
7 | Installation of 400 KVA Transformer at Govt.Polytechnic Bandipora. | Bandipora | R&B | PWD (R&B) | 2020-21 | 11.22 | 11.22 | 68 of 2020 dated 13.02.2020 | 0 | 6 | 0 | 11.22 | 0 | 11.22 | 0 | Funds not received
8 | Repair /Renovation of old Guest House at Govt. Polytechnic Boys Jammu | Jammu | R&B | New work | 2020-21 | 6.7 | 6.7 | No | 0 | 4 | 0 | 6.7 | 0 | 6.7 | 0 | Funds not received
9 | Repair /Renovation of various buildings at Govt. women Polytechnic Jammu | Jammu | R&B | New work | 2020-21 | 7.17 | 7.17 | No | 0 | 4 | 0 | 7.17 | 0 | 7.17 | 0 | Funds not received
10 | Repair /face lifting of Principal Quarter and flooring of Textile Block at Govt. women Polytechnic Srinagar | Srinagar | R&B | New work | 2020-21 | 6.93 | 6.93 | No | 0 | 4 | 0 | 6.93 | 0 | 6.93 | 0 | Funds not received
11 | Conversion of existing "Single Phase Electric Supply" into 3-Phase Supply" for Govt Polytechnic Doda | Doda | R&B | New work | 2020-21 | 0.8 | 0.8 | No | 0 | 0.8 | 0 | 0.8 | 0 | 0.8 | 0 | Funds not received
12 | Providing and fixing of collapsible doors at entrance of each floor (Academic block-II) at KGP Srinagar | Srinagar | R&B | PWD (R&B) | 2019-20 | 3.38 | 3.38 | 628 of 2019 dated:- 07-11-2019 | 0 | 3.38 | 0 | 3.38 | 0 | 3.38 | 0 | Completed ( Funds not received)
| Sub-Total C |  |  |  |  | 100.63 | 102.97 | 0 | 33.97 | 50 | 10.16 | 66.85 | 1.81 | 100.82 | 0
Machinery & Equipments
1 | Upgradation of Machinery & Equipment of Govt. Polytechnic Colleges | J&K | J&K | Not applicable | 2020-21 | 1918.48 | 1918.48 | _ | _ | 1918.48 | 0 | 900 | 300 |  |  | Funds not received
| Sub-Total D |  |  |  |  | 1918.48 | 1918.48 |  | _ | 1918.48 | 0 | 900 | 300
Material Supply
1 | Procurement of Material & Supply for Poytechnics | J&K | J&K | Not applicable | 2020-21 | 100 | 100 | _ | _ | 100 | 0 | 50 | 150 |  |  | Funds not received
| Sub-Total E |  |  |  |  | 100 | 100 |  |  | 100 | 0 | 50 | 150
| G. Total (A+B+C+D+E) |  |  |  |  | 4665.13 | 4666.71 | 0 |  | 3011 | 318.51 | 2106.02

## RE 2020-21 (ITI)
Form B-12
Statement of Ongoing and New works for the finanacial year 2020-21
Department : Skill Development J&K
Office : Directorate of Skill Development, J&K
Demand No. : 34
Major Head : 4250
Sub Major Head : 00
Minor Head : 800
Group Head : 0011
Sub Head : 1644
Detailed Head : 115
Revised Estimates 2020-21 of Capex Budget
S.No | Name of the work/ activity-wise | District | Location | Executing Agency | Project Initiation Year | Orginal Cost of the Project | Revised Cost | Whether AA/TS accorded if Yes , No. & Date | Cummulative Exp. Ending 31st March, 2020 | Approved Capex Budget | Funds released during 2020-21 | Expenditure ending January, 2021 | Anticipated Exp. Ending March 2021 | Proposed Capex Budget for ensuing Year | Com. Ant. Expdt. 03/2021 | Balace reqd | Physical Status ( %age) with Photograph
ITI Sector
Ongoing Works
1 | Construction of W/ shop for Motor Mehanic (MMV) / Plumber Trade & auto mobile service Station at IT R.S.Pora | Jammu | R.S pora | PWD (R&B) | 2015-16 | 93.3 | 93.3 | 201 of 2016 17.03.2016 | 81.86 | 11.44 | 11.44 | 2.86 | 2.86 | 0 | 84.72 | 8.58 | 90% Completed
2 | Construction of Hostel Building at ITI Banihal | Ramban | Banihal | J&K Housing Board | 2014-15 | 86.16 | 86.16 | 178 of 2014 dated:- 21-02-2014 | 77.83 | 8.33 | 8.33 | 0 | 8.33 | 0 | 86.16 | 0 | Finishing work in progress
3 | Construction of first floor to ITI building at ITI Nowshera | Jammu | Nowshera | PWD (R&B) | 2018-19 | 99.9 | 99.9 | 38 of 2019 dated:- 17-01-2019 | 39.06 | 30.42 | 30.42 | 15.21 | 30.42 | 30.42 | 69.48 | 30.42 | Brick work completed. Slab laid .
4 | Construction of Toilet Blocks for Male and Female Trainees at ITI Kathua | Kathua | Kathua | PWD (R&B) | 2018-19 | 11.09 | 11.09 | 36 of 2019 dated:- 17-10-2019 | 3.41 | 7.68 | 7.68 | 1.4 | 7.68 | 0 | 11.09 | 0 | Completed
5 | 100 KVA Servo Stablizer with Panel & Shed at ITI Kishtwar | Kishtwar | Kishtwar | JKPDC | 2018-19 | 16 | 16 | 671 of 2018 dated:- 28-08-2018 | 8.88 | 7.12 | 7.12 | 1.78 | 7.12 | 0 | 16 | 0 | Completed
6 | Construction of Conference / Examination Hall at ITI Anantnag | Anantnag | Anantnag | Engineering Wing, DSD | 2011-12 | 33.06 | 67 | 124 of 2016 dated:- 25-02-2016 | 42.87 | 9 | 9 | 0 | 9 | 15.13 | 51.87 | 15.13 | Completed
7 | Construction of Computer cum Language lab at ITI Anantnag | Anantnag | Anantnag | Engineering Wing, DSD | 2013-14 | 66.97 | 66.97 | 37 of 2014 dated:- 16-01-2014 | 56.06 | 0 | 0 | 0 | 0 | 5.46 | 56.06 | 10.91 | Completed
8 | Construction of Computer cum Language lab at ITI Pattan | Baramulla | Pattan | Engineering Wing, DSD | 2013-14 | 66.97 | 66.97 | 36 of 2014 dated:- 16-01-2014 | 64.32 | 0 | 0 | 0 | 0 | 0 | 64.32 | 2.65 | Completed
9 | Construction of Computer cum Language lab at Women ITI Rohama | Baramulla | Rohama | Engineering Wing, DSD | 2013-14 | 67.32 | 67.32 | 38 of 2014 dated:- 16-01-2014 | 36.19 | 10 | 10 | 0 | 9 | 15.56 | 45.19 | 22.13 | 70% Completed
10 | Construction of Workshop Block at ITI Uri | Baramulla | uri | Engineering Wing, DSD | 2013-14 | 93.81 | 93.81 | 39 of 2014 16.01.2014 | 87.29 | 3.26 | 3.26 | 0 | 3.26 | 3.26 | 90.55 | 3.26 | Completed
11 | Construction of Ist Floor over the existing ground floor of workshop building at ITI Kupwara | Kupwara | Kupwara | Engineering Wing, DSD | 2011-12 | 97.64 | 97.64 | 125 of 2016 dated:- 25-02-2016 | 95.99 | 1.65 | 1.65 | 0 | 1.65 | 0 | 97.64 | 0 | Completed
12 | Construction of Additional Hostel accommodation at ITI Poonch | Poonch | Poonch | Engineering Wing, DSD | 2011-12 | 57.62 | 57.62 | 829 of 2012 dated:- 13-12-2012 | 41.74 | 0 | 0 | 0 | 0 | 7.94 | 41.74 | 15.88 | 90% Completed
13 | Construction of Computer cum Language Lab at ITI Kulgam | Kulgam | kulgam | Engineering Wing, DSD | 2013-14 | 66.97 | 66.97 | 34 of 2014 dated:- 16-01-2014 | 26.68 | 10.01 | 10.01 | 0 | 10 | 30.29 | 36.68 | 30.29 | 60% Completed
14 | Construction of Computer cum Language Lab at ITI Kathua | Kathua | Kathua | Engineering Wing, DSD | 2013-14 | 69.05 | 69.05 | 31 of 2014 16.01.2014 | 49.59 | 0 | 0 | 0 | 0 | 9.73 | 49.59 | 19.46 | 60% Completed
15 | Construction of Toilet Block at ITI Women Jammu | Jammu | Jammu | PWD (R&B) | 2019-20 | 6.1 | 6.1 | 413 of 2019 dated:- 04-07-2019 | 2.66 | 3.44 | 3.44 | 1.61 | 3.44 | 0 | 6.1 | 0 | Completed
16 | Construction of approach road from Main Gate at ITI Bhaderwah | Doda | Bhaderwah | PWD (R&B) | 2019-20 | 14.8 | 14.8 | 629 of 2019 dated:- 07-11-2019 | 4 | 11 | 11 | 2.75 | 11 | 0 | 15 | -0.2 | 50% Completed
17 | Installation of Three Phase Electric Connection at ITI Banihal | Ramban | Banihal | JKPDC | 2019-20 | 6.71 | 6.71 | 412 of 2019 dated:- 04-07-2019 | 0 | 6.71 | 6.71 | 6.71 | 6.71 | 0 | 6.71 | 0 | Completed
18 | Establishment of Conference Hall at Directorate of Technical Education, Jammu | Jammu | Jammu | JKI | 2019-20 | 14.51 | 14.51 | 415 of 2019 dated:- 04-09-2019 | 0 | 12 | 12 | 0 | 6 | 8.51 | 6 | 8.51 | 80% Completed
19 | Construction of Library/Drawing Hall at ITI Bhaddu/Billawar | Kathua | Bhaddu/Billawar | Engineering Wing, DSD | 2011-12 | 36.17 | 36.17 | 827 of 2012 dated:- 13-12-2012 | 29.99 | 0 | 0 | 0 | 0 | 0 | 29.99 | 6.18 | 80% Completed
| Sub-Total A |  |  |  |  | 1004.15 | 1038.09 | 0 | 748.42 | 132.06 | 132.06 | 32.32 | 116.47 | 126.3 | 864.89 | 173.2
New Works
1 | Construction of Boundary Wall and Main Gate of Devry Stones at Govt. ITI Kulgam | Kulgam | Kulgam | J&K Housing Board | 2020-21 | 31.57 | 31.57 | 67 of 2020 dated:- 13-02-2020 | 0 | 20 | 10 | 0 | 10 | 21.57 |  |  | Tendering u/progress
2 | Construction of workshop block at Women ITI Bemina- Phase-II | Srinagar | Bemina | PWD (R&B) | 2020-21 | 82.58 | 82.58 | 681 of 2019 dated:- 03-12-2019 | 0 | 82.58 | 41.29 | 41.29 | 82.58 | 0 |  |  | 90% Completed
3 | Balance cost for completion of 3- storey workshop building and reconstruction of damaged compound walling at ITI Zainakote | Srinagar | Zainakote | J&K Housing Board | 2020-21 | 136 | 136 | No | 0 | 54.85 | 27.43 | 0 | 54.85 | 81.15 |  |  | U/Process
| Sub-Total B |  |  |  |  | 250.15 | 250.15 | 0 | 0 | 157.43 | 78.72 | 41.29 | 147.43 | 102.72
Maintenance of Capital Assets (M&R)
1 | Face lifting of Main building including Repair to toilets & Bathroom of Hostel Building of ITI Hiranagar | Kathua | Hiranagar | PWD (R&B) | 2018-19 | 9.06 | 9.06 | 716 of 2018 dated:- 15-09-2018 | 4.53 | 4.53 | 4.53 | 2.27 | 4.53 | 0 | 9.06 | 0 | Completed
2 | Landscape development of ITI Sopore. Construction of fencing around park proposed in front of administration and women's building | Baramulla | Sopore | PWD (R&B) | 2018-19 | 3.19 | 3.19 | 715 of 2018 dated:- 15-09-2018 | 2.34 | 0.85 | 0.85 | 0 | 0.85 | 0 | 3.19 | 0 | Completed
3 | Dismantling of old abandoned Block at Govt. ITI Samba | Samba | Samba | PWD (R&B) | 2019-20 | 3 | 2.4 | 409 of 2019 dated:- 04-07-2019 | 2.4 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | Completed
4 | Development & Upgradation of parking area at ITI Jammu | Jammu | Jammu | PWD (R&B) | 2020-21 | 10.92 | 10.92 | 350 of 2020 dated:- 29-09-2020 | 0 | 10.92 | 10.92 | 5.46 | 10.92 | 0 | 10.92 | 0 | Concrete/Step work under progress
5 | Facelifting of Admn Block & Workshop Block at Women ITI Jammu | Jammu | Jammu | PWD (R&B) | 2020-21 | 11.92 | 11.92 | 91 of 2021 dated:- 08-02-2021 | 0 | 11.92 | 5.96 | 0 | 11.92 | 0 | 11.92 | 0 | AA accorded
6 | Repair of main block at ITI Doda | Doda | Doda | PWD (R&B) | 2020-21 | 2 | 2 | 298 of 2020 dated:- 09-09-2020 | 0 | 2 | 2 | 0 | 2 | 0 | 2 | 0 | u/ Progress
7 | Repair & Renovation of Workshop / Adm/ Hostel Block ofITI kulgam | Kulgam | Kulgam | PWD (R&B) | 2020-21 | 8.43 | 8.43 | 359 of 2020 dated:- 06-10--2020 | 0 | 8.43 | 8.43 | 0 | 8.43 | 0 | 8.43 | 0 | u/ Process
8 | Facelifting of ITI building at ITI Kangan | Ganderbal | Kangan | PWD (R&B) | 2020-21 | 8.85 | 8.85 | 297 of 2020 dated:- 09-09-2020 | 0 | 8.85 | 8.85 | 0 | 8.85 | 0 | 8.85 | 0 | Completed
9 | Repair of protection wall & Iron fencing grill at ITI Kupwara | Kupwara | Kupwara | PWD (R&B) | 2020-21 | 6.15 | 6.15 | 299 of 2020 dated:- 09-09-2020 | 0 | 6.15 | 6.15 | 0 | 6.15 | 0 | 6.15 | 0 | Work alloted & shall start from 15th Feb
10 | Renovation (including electrification) of Workshop block at ITI K B Pora | Kulgam | KB Pora | PWD (R&B) | 2020-21 | 10 | 10 | 296 of 2020 dated:- 09-09-2020 | 0 | 10 | 10 | 0 | 10 | 0 | 10 | 0 | u/ Progress
11 | Repair/renovation of ITI Jammu | Jammu | Jammu | PWD (R&B) | 2019-20 | 2.37 | 2.37 | 101 of 2020 dated 26.02.2020 | 0 | 2.37 | 2.37 | 0 | 2.37 | 0 | 2.37 | 0 | Completed
12 | Replacement of Secuirity lights ( Sodium Vapour Lights) and Garden lights by way of LED lights in the campus of ITI Anantnag | Anantnag | Anantnag | New Work | 2020-21 | 3.48 | 3.48 | 48 of 2021 dated 25-01-2021 | 0 | 3.48 | 3.48 | 0 | 3.48 | 0 | 3.48 | 0 | Under Process
13 | Augmentation of 25 KVA to 63 KVA DT at Women ITI Kangan | Ganderbal | Kangan | New Work | 2020-21 | 2.75 | 2.75 | 45 of 2021 dated 25-01-2021 | 0 | 2.75 | 2.75 | 0 | 2.75 | 0 | 2.75 | 0 | Under Process
14 | Replacement of Sodium Vapour Lights by way of LED lights in the campus of ITI Seer Hamdan | Anantnag | Seer Hamdan | New Work | 2020-21 | 4.82 | 4.82 | 46 of 2021 dated 25-01-2021 | 0 | 4.82 | 4.82 | 0 | 4.82 | 0 | 4.82 | 0 | Under Process
15 | Repair and renovation of Pre-Fab Structure by way of Ceramic tiles flooring ,Doors and Windows, Electric Works and Painting work at R.S. Pora | Jammu | R.S pora | New Work | 2020-21 | 0.79 | 0.79 | 47 of 2021 dated 25-01-2021 | 0 | 0.79 | 0.79 | 0 | 0.79 | 0 | 0.79 | 0 | Under Process
16 | White Washing / Face lifting of DSD office at Bikram Chowk Jammu | Jammu | Jammu | New Work | 2020-21 | 2 | 2 | No | 0 | 2 | 2 | 0 | 2 | 0 | 2 | 0 | Under Process
17 | White Washing/Face lifting of DSD office at Bemina Srinagar | Srinagar | Bemina | New Work | 2020-21 | 2 | 2 | No | 0 | 2 | 2 | 0 | 2 | 0 | 2 | 0 | Under Process
18 | Renovation of Hostel Block at ITI building, Shopian | Shopian | Shopian | New Work | 2020-21 | 9.68 | 9.68 | 44 of 2021 dated 25-01-2021 | 0 | 9.68 | 9.68 | 0 | 9.68 | 0 | 9.68 | 0 | Under Process
19 | Royality on account of earth filling at ITI Zainakote | Srinagar | Zainakote |  | 2020-21 | 10 | 10 | No | 0 | 10 | 10 | 0 | 3 | 0 | 3 | 7 | Completed
| Sub-Total C |  |  |  |  | 111.41 | 110.81 | 0 | 9.27 | 101.54 | 95.58 | 7.73 | 94.54 |  | 103.81 | 7
Machinery & Equipments
1 | Upgradation of Machinery & Equipment of Govt. ITIs . | J&K | J&K | Not applicable | 2020-21 | 660 | 660 | NA | 0 | 660 | 660 | 0 | 600 | 700
| Sub-Total D |  |  |  |  | 660 | 660 |  | 0 | 660 | 660 | 0 | 600 | 700
Material and supply
1 | Procurement of Material & Supply | J&K | J&K | Not applicable | 2020-21 | 140 | 140 | NA | 0 | 140 | 140 | 0 | 137.5 | 325
| Sub-Total E |  |  |  |  | 140 | 140 |  |  | 140 | 140 | 0 | 137.5 | 325
| G. Total (A+B+C+D+E+F) |  |  |  |  | 2165.71 | 2199.05 |  | 757.69 | 1191.03 | 1106.36 | 81.34 | 1095.94 | 1254.02

## RE 2020-21 (POLY)
Form B-12
Statement of Ongoing and New works for the finanacial year 2020-21
Department : Skill Development J&K
Office : Directorate of Skill Development, J&K
Demand No. : 34
Major Head : 4202
Sub Major Head : 02
Minor Head : 105
Group Head : 0011
Sub Head : 1511
Detailed Head : 115
Revised Estimates 2020-21 of Capex Budget
S.No | Name of the work/ activity-wise | District | Location | Executing Agency | Project Initiation Year | Orginal Cost of the Project | Revised Cost | Whether AA/TS accorded if Yes , No. & Date | Cummulative Exp. Ending 31st March, 2020 | Approved Capex Budget | Funds released during 2020-21 | Expenditure ending January, 2021 | Anticipated Exp. Ending March 2021 | Proposed Capex Budget for ensuing Year | ant. com. Expdt 03/2020 | Balance Cost | Physical Status ( %age) with Photograph
Polytechnic Sector
Ongoing Works
1 | Construction of staff residential quarters at Govt. Polytechnic for Women Jammu. | Jammu | Shakti Nagar | Engineering wing, DSD | 2012-13 | 71 | 71 | 14 Tech-Edu of 2013 17.01.2013 | 65.82 | 5.18 | 5.18 | 0 | 4.5 | 0 | 70.32 | 0.68 | Completed
2 | Repair/renovation of flood damaged auditorium at K.G. Polytechnic, Srinagar. | Srinagar | Gogji Bagh | PWD (R&B) | 2017-18 | 30.16 | 31.33 | 26 of 2020 dated 14.01.2020 | 30.16 | 1.17 | 1.17 | 0.59 | 1.17 | 0 | 31.33 | -1.7764e-15 | Completed
3 | Construction of deficient infrastructure as per AICTE Norms in existing Polytechnics to avoid de-recognition/disapproval of courses. | J&K | J&K | PWD (R&B) | 2017-18 | 148.65 | 148.65 | 914 of 2018 dated:- 14-12-2017 | 104.42 | 44.23 | 44.23 | 12.45 | 43.41 | 0.82 | 147.83 | 0.82 | 95% Completed
4 | Construction of Hostel at Govt Polytechnic Boys Jammu | Jammu | Bikram Chowk | PWD (R&B) | 2018-19 | 717.4 | 717.4 | 15-Edu (Tech) of 2019 dated:- 13-03-2019 | 131.14 | 200 | 200 | 72.42 | 150 | 250 | 281.14 | 436.26 | 40% completed
5 | Construction of Hostel at Govt. Polytechnic at Anantnag(Civil Construction) | Anantnag | Larkipora | JKPCC (proposed) | 2019-20 | 500 | 500 | No | 0 | 80 | 80 | 0 | 0 | 100 | 0 | 500 | U/process
6 | Establishment of Conference Hall at Directorate of Technical Education, Srinagar. | Srinagar | Bemina | JKI | 2019-20 | 16.58 | 16.58 | 414 of 2019 dated 04.09.2019 | 0 | 8.29 | 8.29 | 0 | 0 | 16.58 | 0 | 16.58 | U/process
7 | Construction of Boundary wall at Govt. Polytechnic Budgam. | Budgam | Nowgam | PWD (R&B) | 2018-19 | 54.01 | 54.01 | 674 of 2018 dated:-28-08-2018 | 38.13 | 8.01 | 8.01 | 0 | 0.56 | 0 | 38.69 | 15.32 | 80% Completed
| Sub-Total A |  |  |  |  | 1537.8 | 1538.97 | 0 | 369.67 | 346.88 | 346.88 | 85.46 | 199.64 | 367.4 | 569.31 | 969.66
New Works
1 | Establishment of CIIIT at Govt. Polytechnic (Boys) Jammu | Jammu | Bikram Chowk | PWD (R&B) | 2020-21 | 276.7 | 261.93 | 178 of 2020 dated:- 27-05-2020 | 0 | 261.93 | 255.56 | 86.1 | 255.56 | 0 | 255.56 | 0 | 60% Completed
2 | Establishment of CIIIT at Govt. Polytechnic Baramulla | Baramulla | Kanispora | PWD (R&B) | 2020-21 | 392.52 | 405.36 | 189 of 2020 dated:- 09-06-2020 | 0 | 405.36 | 398.94 | 196.26 | 405.36 | 0 | 405.36 | 0 | completed
3 | Electrification & other minor works of Main building/ workshop building at Govt. Polytechnic Budgam | Budgam | Budgam | JKPCC | 2020-21 | 75 | 75 | 96 of 2021 dated:-10-02-2021 | 0 | 75 | 37.5 | 0 | 75 | 0 |  |  | U/process
| Sub-Total B |  |  |  |  | 744.22 | 742.29 | 0 | 0 | 742.29 | 692 | 282.36 | 735.92 | 0
Maintenance of Capital Assets (M&R)
1 | Repair and Renovation of Principal Quarter at Govt. Polytechnic Boys Jammu. | Jammu | Bikram Chowk | Engineering wing, DSD | 2017-18 | 4.41 | 4.41 | 72 of 2018 dated:- 04-01-2018 | 2.6 | 0 | 0 | 0 | 0 | 1.81 | 2.6 |  | Completed
2 | Repair/Renovation of Conference Hall of Women Polytechnic Jammu. | Jammu | Shakti Nagar | JK SICOP | 2018-19 | 16.53 | 16.53 | 670 of 2018 dated:- 28-08-2018 | 8.9 | 7.63 | 7.63 | 3.82 | 7.63 | 0 | 16.53 |  | 95% Completed. Chairs pending
3 | Renovation of Hostel (New Block) at K G Polytechnic College Gogji Bagh Srinagar. | Srinagar | Gogji Bagh | PWD (R&B) | 2017-18 | 19.12 | 21.46 | 117 of 2020 dated 10.03.2020 | 19.12 | 2.34 | 2.34 | 1.17 | 2.34 | 0 | 21.46 | 0 | completed
4 | Electrification of Internal wiring (3 Phase) to workshop building at Polytechnic Anantnag. | Anantnag | Larkipora | PWD (R&B) | 2020-21 | 10.33 | 10.33 | 212 of 2020 dated 30.06.2020 | 0 | 10.33 | 10.33 | 5.17 | 10.33 | 0 | 10.33 | 0 | Completed
5 | Repair/Renovation of DTE office Srinagar (Phase-II). | Srinagar | Bemina | Engineering wing, DSD | 2018-19 | 3.69 | 3.69 | 719 of 2018 dated:- 15-09-2018 | 3.35 | 0 | 0 | 0 | 0 | 0 | 3.35 | 0 | Completed
6 | Civil Work of Auditorium at KGP Srinagar inculding painting/ polising at Kashmir Govt Polytechnic. | Srinagar | Gogji Bagh | PWD (R&B) | 2020-21 | 10.35 | 10.35 | 27 of 2020 dated 14.01.2020 | 0 | 10.35 | 10.35 | 0 | 10.35 | 0 | 10.35 | 0 | U/Progress
7 | Installation of 400 KVA Transformer at Govt.Polytechnic Bandipora. | Bandipora | Bandipora | PWD (R&B) | 2020-21 | 11.22 | 11.22 | 68 of 2020 dated 13.02.2020 | 0 | 11.22 | 11.22 | 0 | 11.22 | 0 | 11.22 | 0 | 70% completed
8 | Repair /Renovation of old Guest House at Govt. Polytechnic Boys Jammu | Jammu | Jammu | New work | 2020-21 | 6.7 | 6.7 | 50 of 2021 dated 25.01.2021 | 0 | 6.7 | 6.7 | 0 | 6.7 | 0 | 6.7 | 0 | Work alloted
9 | Repair /Renovation of various buildings at Govt. women Polytechnic Jammu | Jammu | Jammu | New work | 2020-21 | 7.17 | 7.17 | 49 of 2021 dated 25.01.2021 | 0 | 7.17 | 7.17 | 0 | 7.17 | 0 | 7.17 | 0 | Work alloted
10 | Repair /face lifting of Principal Quarter and flooring of Textile Block at Govt. women Polytechnic Srinagar | Srinagar | Bemina | New work | 2020-21 | 6.93 | 6.93 | 51 of 2021 dated:- 25-01-2021 | 0 | 6.93 | 6.93 | 0 | 6.93 | 0 | 6.93 | 0 | Work alloted
11 | Conversion of existing "Single Phase Electric Supply" into 3-Phase Supply" for Govt Polytechnic Doda | Doda | Doda | New work | 2020-21 | 0.44 | 0.44 | 69 of 2021 dated:- 01-02-2021 | 0 | 0.8 | 0.44 | 0 | 0.44 | 0 | 0.44 | 0 | Work alloted
12 | Providing and fixing of collapsible doors at entrance of each floor (Academic block-II) at KGP Srinagar | Srinagar | Gojibagh | PWD (R&B) | 2019-20 | 3.38 | 3.38 | 628 of 2019 dated:- 07-11-2019 | 0 | 3.38 | 3.38 | 0 | 3.38 | 0 | 3.38 | 0 | 50% completed | .36+
| Sub-Total C |  |  |  |  | 100.27 | 102.61 | 0 | 33.97 | 66.85 | 66.49 | 10.16 | 66.49 | 1.81 | 100.46 | 0
Machinery & Equipments
1 | Upgradation of Machinery & Equipment of Govt. Polytechnic Colleges | J&K | J&K | Not applicable | 2020-21 | 1100 | 1100 | _ | _ | 1100 | 1100 | 65.5 | 1100 | 300
| Sub-Total D |  |  |  |  | 1100 | 1100 |  | _ | 1100 | 1100 | 65.5 | 1100 | 300
Material Supply
1 | Procurement of Material & Supply for Poytechnics | J&K | J&K | Not applicable | 2020-21 | 50 | 50 | _ | _ | 50 | 50 | 0 | 50 | 150
| Sub-Total E |  |  |  |  | 50 | 50 |  |  | 50 | 50 | 0 | 50 | 150
| G. Total (A+B+C+D+E) |  |  |  |  | 3532.29 | 3533.87 |  |  | 2306.02 | 2255.37 | 443.48 | 2152.05

## GNO
Revised Capex Budget 2020-21/ Budget Estimates 2021-22 (Rs. in lakhs)
Sector/ Head of Development : POLYTECHNIC SECTOR/ DIRECTOR , SKILL DEVELOPMENT
S.No. | Name of sector/ OBJECT OF EXPENDITURE | Approved allocation 2020-21 | Funds released | Expdt. ending January2020 | Anticipated Exp. Ending March 2021 | Proposed Capex Budget for ensuing Year (2021-22)
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | WORKS (ongoing) | 346.88 | 346.88 | 85.46 | 199.64 | 367.4
2 | WORKS (New) | 742.29 | 692 | 282.36 | 735.92 | 0
3 | LAND COMPENSATION | 0 | 0 | 0 | 0 | 0
4 | MAINTENANCE AND REPAIRS (Maintenance of Capital Assets) | 66.85 | 66.49 | 10.16 | 66.49 | 100
5 | MATERIAL AND SUPPLIES | 50 | 50 | 0 | 50 | 150
6 | MACHINERY AND EQUIPMENT | 1100 | 1100 | 65.5 | 1100 | 300
| TOTAL (A) | 2306.02 | 2255.37 | 443.48 | 2152.05 | 917.4
Sector/ Head of Development : Craftsmanship/ITI SECTOR/ DIRECTOR SKILL DEVELOPMENT
1 | WORKS (ongoing) | 132.06 | 132.06 | 32.32 | 116.47 | 126.3
2 | WORKS (New) | 157.43 | 78.72 | 41.29 | 147.43 | 102.72
4 | LAND COMPENSATION | 0 | 0 | 0 | 0 | 100
5 | MAINTENANCE AND REPAIRS (Maintenance of Capital Assets) | 101.54 | 95.58 | 7.73 | 94.54 | 100
6 | MATERIAL AND SUPPLIES (Improvement of existing ITIs) | 140 | 140 | 0 | 137.5 | 325
7 | MACHINERY AND EQUIPMENT (Modernization of ITIs) | 660 | 660 | 0 | 600 | 700
| TOTAL (B) | 1191.03 | 1106.36 | 81.34 | 1095.94 | 1454.02
| Grand Total (A+B) | 3497.05 | 3361.73 | 524.82 | 3247.99 | 2371.42